## Tickets
			Dates
ID	Subject	Type	Created	Started	Closed	Effort (hours)	Load Failure
1	The german localization is missing	Feature	17.07.14	19.07.14	19.07.2014	1	0
2	Internal Server Error in HAC - Update Running System	Bug	17.07.14	20.07.14	20.07.2014	1,5	1
3	Run the deployment scripts without updating the system	Feature	17.07.14	20.07.14	18.08.14	6,25	1
7	Write Troubleshooting PWikipage	Task	07.06.14	28.07.14	28.07.2014	1	0
8	Write the "How to Contribute" wiki page	Task	07.06.14	28.07.14	28.07.2014	0,75	0
9	Document the examples of the deployment scripts	Task	07.06.14	28.07.14	28.07.2014	0,5	0
6	Upload screenshots	Task	07.06.14	28.07.14	28.07.2014	0,25	0
13	Deployment Scripts which run during the Initialization Process	Feature	04.08.14	07.08.14	07.08.14	2,75	0
5	Improve the logging in HAC	Feature	20.07.14	09.08.14	09.08.14	6	1
14	Contraints for the deployment scripts	Feature	07.08.14	18.08.14	18.08.14	12	0
10	Integrate PMD, Findbugs and Chekstyle in the build	Task	29.07.14	08.09.14	27.01.14	21,25	0
17	Junit Tenant Restriction doesn't work in databases with one tenant	Bug	24.08.14	03.10.14	03.10.14	1,25	1
16	Init Deployment Scripts are imported with USA Locale	Bug	24.08.14	03.10.14	03.10.14	2,5	1
15	ant updatesystem and yunitint must fail if the was an error	Feature	18.08.14	03.10.14	04.10.14	5	1
4	CronJob Starter for the Beanshell Scripts	Feature	17.07.14	06.10.14	06.10.14	0,5	0
19	Cobertura doesn't work in a fresh installed environment	Bug	03.10.14	06.10.14	20.10.14	17	1
11	Write Unit and Integration Tests	Task	27.09.14	05.10.14	26.01.15	25,5	0
20	UpdatingSystemExtensionContextLoggingTest fails in a undeterministic way	Bug	05.10.14	26.01.15	26.01.15	1,5	1
22	Beanshell Shell Service muss log the return value of the script	Bug	12.11.14	27.01.15	27.01.15	1	1
18	Migrate the extension to Hybris 5.2	Feature	08.09.14	31.01.15	07.02.15	10,25	0
12	Junit Tenant: Error when the extension is desactivated	Bug	08.04.14	07.02.15	15.02.15	3,75	1
24	Support Insert SQL Scripts	Feature	30.01.15	07.02.15	07.02.15	1,5	0
23	SQL Scripts: The changes in the database aren't reflected on the models	Bug	25.01.15	08.02.15	08.02.15	4,25	1
25	Deployment Scripts with Medias doesn'T work	Bug	09.02.15	15.02.15	15.03.15	1,75	1
26	Alter Table SQL Statements must be allowed	Feature	16.02.15	15.03.15	17.03.15	2	0
27	The JaloSqlScriptService must not commit the statement	Bug	15.03.15	17.03.15	17.03.15	0	1
28	Test SQL Scripts don't work in MySQL	Bug	18.03.15	14.05.15	14.05.15	1,75	1
29	Fail to detect that the last script had an error	Bug	18.03.15	12.05.15	13.05.15	1,5	1
30	Hybris 5.3: ant junitinit doesn't work	Bug	19.03.15	13.05.15	13.05.15	0,75	1
31	Jenkins failing JUnit test SqlScriptsTest.testScriptsWithCreateTable()	Bug	20.05.15	20.05.15	01.09.15	3,75	1
32	Run Groovy Scripts	Feature	24.06.15	02.09.15	06.09.15	2,5	0
33	Accept naming the environments with a different case or with blank spaces	Feature	21.07.15	01.09.15	01.09.15	0,75	1
34	Show error when the required configuration properties are missing	Bug	11.08.15	06.09.15	06.09.15	1	1
35	Save the stacktrace in the script execution	Feature	01.09.15	06.09.15	17.09.15	4,5	0