## Tickets
			Dates
ID	Subject	Type	Created	Started	Closed	Effort (hours)	Load Failure
1	The german localization is missing	Feature	17.07.14	19.07.14	19.07.2014	1	0
2	Internal Server Error in HAC - Update Running System	Bug	17.07.14	20.07.14	20.07.2014	1,5	1
3	Run the deployment scripts without updating the system	Feature	17.07.14	20.07.14	18.08.14	6,25	1
7	Write Troubleshooting PWikipage	Task	07.06.14	28.07.14	28.07.2014	1	0
8	Write the "How to Contribute" wiki page	Task	07.06.14	28.07.14	28.07.2014	0,75	0
9	Document the examples of the deployment scripts	Task	07.06.14	28.07.14	28.07.2014	0,5	0
6	Upload screenshots	Task	07.06.14	28.07.14	28.07.2014	0,25	0
13	Deployment Scripts which run during the Initialization Process	Feature	04.08.14	07.08.14	07.08.14	2,75	0
5	Improve the logging in HAC	Feature	20.07.14	09.08.14	09.08.14	6	1
14	Contraints for the deployment scripts	Feature	07.08.14	18.08.14	18.08.14	12	0
10	Integrate PMD, Findbugs and Chekstyle in the build	Task	29.07.14	08.09.14	03.10.14	20,25	0